## Detailed Gantt Chart
Task ID | Task / Sub-task | Duration (Days) | Start Day | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30
T1 | Project Planning
T1.1 | Understand coursework brief | 1 | 1 | bar: Day 1
T1.2 | Define objectives & deliverables | 1 | 2 | bar: Day 2
T1.3 | Prepare project schedule | 1 | 3 | bar: Day 3
T2 | Data Collection & Preparation
T2.1 | Import datasets | 1 | 4 | bar: Day 4
T2.2 | Inspect datasets | 1 | 5 | bar: Day 5
T2.3 | Rename columns | 1 | 6 | bar: Day 6
T2.4 | Handle missing values | 1 | 7 | bar: Day 7
T2.5 | Merge datasets | 2 | 8 | bar: Day 8 to Day 9
T3 | Exploratory Data Analysis
T3.1 | Generate trend graphs | 1 | 10 | bar: Day 10
T3.2 | Summarise observations | 1 | 11 | bar: Day 11
T4 | Statistical Analysis
T4.1 | Correlation analysis | 1 | 12 | bar: Day 12
T4.2 | VIF analysis | 1 | 13 | bar: Day 13
T4.3 | Feature selection | 1 | 14 | bar: Day 14
T5 | Predictive Modelling
T5.1 | Train Linear Regression | 1 | 15 | bar: Day 15
T5.2 | Train Ridge Regression | 1 | 16 | bar: Day 16
T5.3 | Train Lasso Regression | 1 | 17 | bar: Day 17
T5.4 | Evaluate models | 2 | 18 | bar: Day 18 to Day 19
T6 | Forecasting & Business Analysis
T6.1 | Generate forecasts | 1 | 20 | bar: Day 20
T6.2 | Regional risk analysis | 1 | 21 | bar: Day 21
T6.3 | Develop recommendations | 1 | 22 | bar: Day 22
T7 | Documentation
T7.1 | Write report | 3 | 23 | bar: Day 23 to Day 25
T7.2 | Review & proofread | 2 | 26 | bar: Day 26 to Day 27
T7.3 | GitHub upload & submission | 1 | 28 | bar: Day 28